## Cash Flow calculation
| COSTS INVOICE |  |  |  |  | CASH FLOW OUT |  |  |  |  | COST OF DEBT/REVENUE FROM CREDIT | REVENUE INVOICE | CASH FLOW IN FROM OWNER | DELTA PERCENTAGE OF CONSTRUCTION WORKS COMPLETION | DELTA CASH FLOW | CUMULATED CASH FLOW
| CORPORATE OVERHEAD | HUMAN RESOURCES | MATERIALS | SUBCONTRACTORS | INSURANCE | CORPORATE OVERHEAD | HUMAN RESOURCES | MATERIALS | SUBCONTRACTORS | INSURANCE
2021-05-01 | 218016000 | 28342080 | 0 | 0 | 0 | 218016000 | 28342080 | 0 | 0 | 0 | 0 | 109777120386.494 | 0 | 0% | -246358080 | -246358080
2021-06-01 | 4796352000 | 1589881680 | 0 | 0 | 0 | 4796352000 | 1589881680 | 0 | 0 | 0 | -1231790.4 | 0 | 109777120386.494 | 0% | 103389654916.094 | 103143296836.094
2021-07-02 | 4796352000 | 1818798480 | 0 | 0 | 0 | 4796352000 | 1818798480 | 0 | 0 | 0 | 172249305.7163 | 0 | 0 | 0% | -6442901174.2837 | 96700395661.8103
2021-08-02 | 4796352000 | 2312877240 | 2823390412 | 0 | 0 | 4796352000 | 2312877240 | 0 | 0 | 0 | 161489660.7552 | 0 | 0 | 0% | -6947739579.2448 | 89752656082.5655
2021-09-02 | 4796352000 | 802298880 | 1427921588 | 0 | 272520000 | 4796352000 | 802298880 | 0 | 0 | 272520000 | 149886935.6579 | 0 | 0 | 0% | -5721283944.3421 | 84031372138.2234
2021-10-03 | 4578336000 | 211736340 | 0 | 39930153600 | 0 | 4578336000 | 211736340 | 2823390412 | 0 | 0 | 140332391.4708 | 44813334003.2112 | 0 | 5.103% | -7473130360.5292 | 76558241777.6942
2021-11-03 | 4796352000 | 546705353 | 8819837280 | 23946709500 | 5450400000 | 4796352000 | 546705353 | 1427921588 | 0 | 5450400000 | 127852263.7687 | 26875225721.6804 | 0 | 3.06% | -12093526677.2313 | 64464715100.463
2021-12-04 | 5014368000 | 2490447204 | 48236040000 | 60328635000 | 0 | 5014368000 | 2490447204 | 0 | 39930153600 | 0 | 107656074.2178 | 67706407976.673 | 44813334003.2112 | 7.71% | -2513978726.571 | 61950736373.892
2022-01-04 | 4578336000 | 2740732770 | 62570592000 | 87312798900 | 0 | 4578336000 | 2740732770 | 8819837280 | 23946709500 | 0 | 103457729.7444 | 97990547671.2444 | 26875225721.6804 | 11.16% | -13106932098.5752 | 48843804275.3168
2022-02-04 | 4360320000 | 3063528858 | 27252000000 | 91419223200 | 0 | 4360320000 | 3063528858 | 48236040000 | 60328635000 | 0 | 81569153.1398 | 102599159137.1117 | 67706407976.673 | 11.68% | -48200546728.1873 | 643257547.1295
2022-03-07 | 5014368000 | 3857254913 | 86871200400 | 52964337000 | 0 | 5014368000 | 3857254913 | 62570592000 | 87312798900 | 0 | 1074240.1037 | 59441507488.7074 | 97990547671.2444 | 6.768% | -60763391901.6519 | -60120134354.5224
2022-04-07 | 4578336000 | 3526462434 | 77395680000 | 13645611000 | 0 | 4578336000 | 3526462434 | 27252000000 | 91419223200 | 0 | -300600671.7726 | 15314374433.5833 | 102599159137.1117 | 1.744% | -24477463168.6609 | -84597597523.1833
2022-05-08 | 4796352000 | 3685045673 | 0 | 14799945600 | 0 | 4796352000 | 3685045673 | 86871200400 | 52964337000 | 0 | -422987987.6159 | 16609876136.3682 | 59441507488.7074 | 1.891% | -89298415571.9085 | -173896013095.0919
2022-06-08 | 4796352000 | 2819696566 | 0 | 23545368000 | 0 | 4796352000 | 2819696566 | 77395680000 | 13645611000 | 0 | -869480065.4755 | 26424802944.2221 | 15314374433.5833 | 3.009% | -84212445197.8922 | -258108458292.9841
2022-07-09 | 4578336000 | 2399145301 | 0 | 22475124000 | 0 | 4578336000 | 2399145301 | 0 | 14799945600 | 0 | -1290542291.4649 | 25223675537.6665 | 16609876136.3682 | 2.872% | -6458093056.0967 | -264566551349.0808
2022-08-09 | 5014368000 | 2552690772 | 0 | 24615612000 | 0 | 5014368000 | 2552690772 | 0 | 23545368000 | 0 | -1322832756.7454 | 27625930350.7776 | 26424802944.2221 | 3.146% | -6010456584.5233 | -270577007933.6041
2022-09-09 | 4796352000 | 704696166 | 0 | 15009521800 | 0 | 4796352000 | 704696166 | 0 | 22475124000 | 0 | -1352885039.668 | 181360040427.1546 | 25223675537.6665 | 20.65% | -4105381668.0015 | -274682389601.6056
2022-10-10 | 4578336000 | 876221586 | 0 | 2066846560 | 0 | 4578336000 | 876221586 | 0 | 24615612000 | 0 | -1373411948.008 | 184786579204.3969 | 27625930350.7776 | 21.04% | -3817651183.2304 | -278500040784.836
2022-11-10 | 4796352000 | 1222120269 | 0 | 456636248 | 0 | 4796352000 | 1222120269 | 0 | 15009521800 | 0 | -1392500203.9242 | 849890433.5723 | 181360040427.1546 | 0.09677% | 158939546154.2304 | -119560494630.6056
2022-12-11 | 4796352000 | 2027517419 | 0 | 144603200 | 0 | 4796352000 | 2027517419 | 0 | 2066846560 | 0 | -597802473.153 | 595611625.5826 | 184786579204.3969 | 0.06782% | 175298060752.2439 | 55737566121.6383
2023-01-11 | 2834208000 | 812364749 | 0 | 0 | 0 | 2834208000 | 812364749 | 0 | 456636248 | 0 | 93081735.4231 | 109777120386.494 | 849890433.5723 | 0% | -3160236828.0046 | 52577329293.6337
2023-02-11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144603200 | 0 | 87804139.9204 | 0 | 595611625.5826 | 0% | 538812565.5029 | 53116141859.1367
2023-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88703956.9048 | 0 | 0 | 0% | 88703956.9048 | 53204845816.0414
2023-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 88852092.5128 | 0 | 0 | 0% | 88852092.5128 | 53293697908.5542
2023-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 89000475.5073 | 0 | 109777120386.494 | 0% | 109866120862.0013 | 163159818770.5555
2023-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 163159818770.5555
2023-07-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0% | 0 | 163159818770.5555
TOTAL | 93310848000 | 40088564733 | 315396661680 | 472661125608 | 5722920000 | 93310848000 | 40088564733 | 315396661680 | 472661125608 | 5722920000 | -7431265073.3846 |  |  | 100%
CHECK TOTAL | 93310848000 | 40088564733 | 315396661680 | 472661125608 | 5722920000 | 93310848000 | 40088564733 | 315396661680 | 472661125608 | 5722920000
TOTAL PRICE | 1.0978e+12

## Cash flow graph
| CASH FLOW OUT | [6 empty] | COST OF DEBT/REVENUE FROM CREDIT | CASH FLOW IN FROM OWNER | TOTAL | CUMULATED CASH FLOW IN | DELTA CASH FLOW | CUMULATED CASH FLOW
| CORPORATE OVERHEAD | HUMAN RESOURCES | MATERIALS | SUBCONTRACTORS | INSURANCE | TOTAL | CUMULATED CASH FLOW OUT
2021-05-01 | 218016000 | 28342080 | 0 | 0 | 0 | 246358080 | 246358080 | 0 | 0 | 0 | 0 | -246358080 | -246358080
2021-06-01 | 4796352000 | 1589881680 | 0 | 0 | 0 | 6387465470.4 | 6633823550.4 | -1231790.4 | 109777120386.494 | 109777120386.494 | 109777120386.494 | 103389654916.094 | 103143296836.094
2021-07-02 | 4796352000 | 1818798480 | 0 | 0 | 0 | 6615150480 | 13248974030.4 | 172249305.7163 | 0 | 172249305.7163 | 109949369692.2103 | -6442901174.2837 | 96700395661.8103
2021-08-02 | 4796352000 | 2312877240 | 0 | 0 | 0 | 7109229240 | 20358203270.4 | 161489660.7552 | 0 | 161489660.7552 | 110110859352.9655 | -6947739579.2448 | 89752656082.5655
2021-09-02 | 4796352000 | 802298880 | 0 | 0 | 272520000 | 5871170880 | 26229374150.4 | 149886935.6579 | 0 | 149886935.6579 | 110260746288.6234 | -5721283944.3421 | 84031372138.2234
2021-10-03 | 4578336000 | 211736340 | 2823390412 | 0 | 0 | 7613462752 | 33842836902.4 | 140332391.4708 | 0 | 140332391.4708 | 110401078680.0942 | -7473130360.5292 | 76558241777.6942
2021-11-03 | 4796352000 | 546705353 | 1427921588 | 0 | 5450400000 | 12221378941 | 46064215843.4 | 127852263.7687 | 0 | 127852263.7687 | 110528930943.863 | -12093526677.2313 | 64464715100.463
2021-12-04 | 5014368000 | 2490447204 | 0 | 39930153600 | 0 | 47434968804 | 93499184647.4 | 107656074.2178 | 44813334003.2112 | 44920990077.429 | 155449921021.292 | -2513978726.571 | 61950736373.892
2022-01-04 | 4578336000 | 2740732770 | 8819837280 | 23946709500 | 0 | 40085615550 | 133584800197.4 | 103457729.7444 | 26875225721.6804 | 26978683451.4248 | 182428604472.7168 | -13106932098.5752 | 48843804275.3168
2022-02-04 | 4360320000 | 3063528858 | 48236040000 | 60328635000 | 0 | 115988523858 | 249573324055.4 | 81569153.1398 | 67706407976.673 | 67787977129.8127 | 250216581602.5295 | -48200546728.1873 | 643257547.1295
2022-03-07 | 5014368000 | 3857254913 | 62570592000 | 87312798900 | 0 | 158755013813 | 408328337868.4 | 1074240.1037 | 97990547671.2444 | 97991621911.3481 | 348208203513.8776 | -60763391901.6519 | -60120134354.5224
2022-04-07 | 4578336000 | 3526462434 | 27252000000 | 91419223200 | 0 | 127076622305.7726 | 535404960174.1726 | -300600671.7726 | 102599159137.1117 | 102599159137.1117 | 450807362650.9893 | -24477463168.6609 | -84597597523.1833
2022-05-08 | 4796352000 | 3685045673 | 86871200400 | 52964337000 | 0 | 148739923060.6159 | 684144883234.7886 | -422987987.6159 | 59441507488.7074 | 59441507488.7074 | 510248870139.6967 | -89298415571.9085 | -173896013095.0919
2022-06-08 | 4796352000 | 2819696566 | 77395680000 | 13645611000 | 0 | 99526819631.4755 | 783671702866.264 | -869480065.4755 | 15314374433.5833 | 15314374433.5833 | 525563244573.28 | -84212445197.8922 | -258108458292.9841
2022-07-09 | 4578336000 | 2399145301 | 0 | 14799945600 | 0 | 23067969192.4649 | 806739672058.729 | -1290542291.4649 | 16609876136.3682 | 16609876136.3682 | 542173120709.6481 | -6458093056.0967 | -264566551349.0808
2022-08-09 | 5014368000 | 2552690772 | 0 | 23545368000 | 0 | 32435259528.7454 | 839174931587.4744 | -1322832756.7454 | 26424802944.2221 | 26424802944.2221 | 568597923653.8702 | -6010456584.5233 | -270577007933.6041
2022-09-09 | 4796352000 | 704696166 | 0 | 22475124000 | 0 | 29329057205.668 | 868503988793.1423 | -1352885039.668 | 25223675537.6665 | 25223675537.6665 | 593821599191.5367 | -4105381668.0015 | -274682389601.6056
2022-10-10 | 4578336000 | 876221586 | 0 | 24615612000 | 0 | 31443581534.008 | 899947570327.1504 | -1373411948.008 | 27625930350.7776 | 27625930350.7776 | 621447529542.3143 | -3817651183.2304 | -278500040784.836
2022-11-10 | 4796352000 | 1222120269 | 0 | 15009521800 | 0 | 22420494272.9242 | 922368064600.0746 | -1392500203.9242 | 181360040427.1546 | 181360040427.1546 | 802807569969.4689 | 158939546154.2304 | -119560494630.6056
2022-12-11 | 4796352000 | 2027517419 | 0 | 2066846560 | 0 | 9488518452.153 | 931856583052.2277 | -597802473.153 | 184786579204.3969 | 184786579204.3969 | 987594149173.8658 | 175298060752.2439 | 55737566121.6383
2023-01-11 | 2834208000 | 812364749 | 0 | 456636248 | 0 | 4103208997 | 935959792049.2277 | 93081735.4231 | 849890433.5723 | 942972168.9954 | 988537121342.8612 | -3160236828.0046 | 52577329293.6337
2023-02-11 | 0 | 0 | 0 | 144603200 | 0 | 144603200 | 936104395249.2277 | 87804139.9204 | 595611625.5826 | 683415765.5029 | 989220537108.3641 | 538812565.5029 | 53116141859.1367
2023-03-14 | 0 | 0 | 0 | 0 | 0 | 0 | 936104395249.2277 | 88703956.9048 | 0 | 88703956.9048 | 989309241065.2689 | 88703956.9048 | 53204845816.0414
2023-04-14 | 0 | 0 | 0 | 0 | 0 | 0 | 936104395249.2277 | 88852092.5128 | 0 | 88852092.5128 | 989398093157.7817 | 88852092.5128 | 53293697908.5542
2023-05-15 | 0 | 0 | 0 | 0 | 0 | 0 | 936104395249.2277 | 89000475.5073 | 109777120386.494 | 109866120862.0013 | 1.0993e+12 | 109866120862.0013 | 163159818770.5555
2023-06-15 | 0 | 0 | 0 | 0 | 0 | 0 | 936104395249.2277 | 0 | 0 | 0 | 1.0993e+12 | 0 | 163159818770.5555
2023-07-16 | 0 | 0 | 0 | 0 | 0 | 0 | 936104395249.2277 | 0 | 0 | 0 | 1.0993e+12 | 0 | 163159818770.5555

## Cost calculation
Task Name | Start | Finish | Resource Names | Work | Duration | Cost | 2021-05-01 | 2021-06-01 | 2021-07-02 | 2021-08-02 | 2021-09-02 | 2021-10-03 | 2021-11-03 | 2021-12-04 | 2022-01-04 | 2022-02-04 | 2022-03-07 | 2022-04-07 | 2022-05-08 | 2022-06-08 | 2022-07-09 | 2022-08-09 | 2022-09-09 | 2022-10-10 | 2022-11-10 | 2022-12-11 | 2023-01-11 | 2023-02-11 | 2023-03-14 | 2023-04-14 | 2023-05-15 | 2023-06-15 | 2023-07-16 | TOTAL | CHECK TOTAL
PROJECT | Mon 31/05/21 | Wed 18/01/23 |  | 24.448,32 hrs | 427,12 days? | [28 empty] | 0 | 0
|  |  | Overhead |  |  | 93310848000 | 218016000 | 4796352000 | 4796352000 | 4796352000 | 4796352000 | 4578336000 | 4796352000 | 5014368000 | 4578336000 | 4360320000 | 5014368000 | 4578336000 | 4796352000 | 4796352000 | 4578336000 | 5014368000 | 4796352000 | 4578336000 | 4796352000 | 4796352000 | 2834208000 | [6 empty] | 93310848000 | 0
Start | Mon 31/05/21 | Mon 31/05/21 |  | 0 hrs | 0 days | [28 empty] | 0 | 0
INITIALIZATION | Mon 31/05/21 | Fri 29/10/21 |  | 3.156 hrs | 109,5 days? | [28 empty] | 0 | 0
START-UP | Mon 31/05/21 | Tue 08/06/21 |  | 56 hrs | 7 days | [28 empty] | 0 | 0
Contract finalization and signature | Mon 31/05/21 | Tue 01/06/21 | Project manager | 16 hrs | 2 days | 56684160 | 28342080 | 28342080 | [25 empty] | 56684160 | 0
Detailed Planning | Wed 02/06/21 | Tue 08/06/21 | Project manager | 40 hrs | 5 days | 141710400 |  | 141710400 | [25 empty] | 141710400 | 0
ENGINEERING PHASE | Wed 09/06/21 | Fri 29/10/21 |  | 3.100 hrs | 102,5 days? | [28 empty] | 0 | 0
Detailed Engineering - Process | Mon 05/07/21 | Thu 22/07/21 | Project engineer[200%];Specialized engineer[200%] | 350 hrs | 13,13 days | 848899800 |  |  | 848899800 | [24 empty] | 848899800 | 0
Detailed Engineering - Layout | Thu 22/07/21 | Thu 05/08/21 | Project engineer[200%];Specialized engineer[200%] | 260 hrs | 9,38 days? | 628158600 |  |  | 463011480 | 165147120 | [23 empty] | 628158600 | 0
Detailed Engineering - Utilities | Thu 05/08/21 | Mon 16/08/21 | Project engineer[200%];Specialized engineer[200%] | 210 hrs | 7,5 days? | 506887200 |  |  |  | 506887200 | [23 empty] | 506887200 | 0
Industrial Building Design | Wed 09/06/21 | Mon 05/07/21 | Project engineer[200%];Specialized engineer[200%] | 510 hrs | 18,75 days? | 1234515600 |  | 1120602240 | 113913360 | [24 empty] | 1234515600 | 0
Line manufacturing ICT system specification & development | Mon 16/08/21 | Mon 20/09/21 | Software developer[200%];Software engineer[300%] | 610 hrs | 25 days | 1249504200 |  |  |  | 829823400 | 419680800 | [22 empty] | 1249504200 | 0
|  |  | Line manufacturing ICT system[1] | 610 hrs | 25 days | 4251312000 |  |  |  | 2823390412 | 1427921588 | [22 empty] | 4251312000 | 0
Approval of engineering by the client | Tue 03/08/21 | Tue 31/08/21 | Owner | 160 hrs | 20 days | 0 |  |  |  | 0 | [23 empty] | 0 | 0
Permits and authorizations from local authorities | Fri 25/06/21 | Fri 29/10/21 | Project engineer[200%];Specialized engineer[200%];Local Authorities | 1.000 hrs | 90 days | 675849600 |  | 122088960 | 139530240 | 383163120 | 31067280 | 0 | [21 empty] | 675849600 | 0
WORK IN ITALY | Mon 05/07/21 | Thu 18/08/22 |  | 9.016 hrs | 293,23 days? | [28 empty] | 0 | 0
PURCHASE CIVIL WORKS | Mon 05/07/21 | Thu 19/08/21 |  | 120 hrs | 33 days? | [28 empty] | 0 | 0
Request for proposals | Mon 05/07/21 | Thu 08/07/21 | Purchasing agent[200%] | 40 hrs | 2,5 days? | 76305600 |  |  | 76305600 | [24 empty] | 76305600 | 0
Collection of proposals | Thu 08/07/21 | Thu 05/08/21 |  | 0 hrs | 20 days | 0 | [27 empty] | 0 | 0
Competitive proposal analysis | Mon 16/08/21 | Wed 18/08/21 | Project engineer[200%];Purchasing agent[200%] | 64 hrs | 2,75 days | 143890560 |  |  |  | 143890560 | [23 empty] | 143890560 | 0
Orders | Wed 18/08/21 | Thu 19/08/21 | Purchasing agent[200%] | 16 hrs | 1 day | 30522240 |  |  |  | 30522240 | [23 empty] | 30522240 | 0
PURCHASE MACHINES | Mon 16/08/21 | Wed 15/09/21 |  | 120 hrs | 21,6 days? | [28 empty] | 0 | 0
Request for proposals | Mon 16/08/21 | Thu 19/08/21 | Purchasing agent[200%] | 40 hrs | 2,5 days? | 76305600 |  |  |  | 76305600 | [23 empty] | 76305600 | 0
Collection of proposals | Wed 18/08/21 | Wed 15/09/21 |  | 0 hrs | 20 days | 0 | [27 empty] | 0 | 0
Competitive proposal analysis | Mon 06/09/21 | Wed 08/09/21 | Project engineer[200%];Purchasing agent[200%] | 64 hrs | 2 days | 143890560 |  |  |  |  | 143890560 | [22 empty] | 143890560 | 0
Orders | Tue 07/09/21 | Wed 08/09/21 | Purchasing agent[200%] | 16 hrs | 1 day | 30522240 |  |  |  |  | 30522240 | [22 empty] | 30522240 | 0
EQUIPMENT MANUFACTURING | Wed 08/09/21 | Wed 09/03/22 |  | 4.888 hrs | 130 days | [28 empty] | 0 | 0
CNC machine (single-spindle and double-spindle) | Wed 08/09/21 | Wed 09/02/22 | Double-spindle CNC machine[11];Single-spindle CNC machine[3];Supplier | 880 hrs | 110 days | 177683040000 | [9 empty] | 27252000000 | 73035360000 | 77395680000 | [15 empty] | 177683040000 | 0
Washing station | Wed 08/09/21 | Wed 15/12/21 | Final washing station[1];Intermediate washing station[1];Supplier | 560 hrs | 70 days | 40878000000 | [7 empty] | 40878000000 | [19 empty] | 40878000000 | 0
Drilling machine | Wed 08/09/21 | Thu 09/12/21 | Drilling machine[1];Supplier | 528 hrs | 66 days | 7358040000 | [7 empty] | 7358040000 | [19 empty] | 7358040000 | 0
Assembly station | Wed 08/09/21 | Wed 26/01/22 | Assembly station[2];Supplier | 800 hrs | 100 days | 59954400000 | [8 empty] | 59954400000 | [18 empty] | 59954400000 | 0
Gantry loaders and robotized arms (total values) | Wed 08/09/21 | Wed 19/01/22 | Gantry loader (including robots)[1];Supplier | 760 hrs | 95 days | 2616192000 | [8 empty] | 2616192000 | [18 empty] | 2616192000 | 0
Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Wed 08/09/21 | Wed 09/03/22 | Lift/lower component[1];Manipulator[2];Overhead conveyor[1];Powered conveyor[1];Rotating table[7];Supplier | 1.040 hrs | 130 days | 13835840400 | [10 empty] | 13835840400 | [16 empty] | 13835840400 | 0
Metal foodbridges and protection grids (total values) | Wed 08/09/21 | Wed 03/11/21 | Metal footbridge[1];Protection grids including doors[1];Supplier | 320 hrs | 40 days | 8819837280 | [6 empty] | 8819837280 | [20 empty] | 8819837280 | 0
PRE- ERECTION | Thu 09/12/21 | Thu 18/08/22 | Formation course (risk mitigation) | 3.888 hrs | 180 days | 13626000 | [6 empty] | 13626000 | [20 empty] | 13626000
|  |  | Insurance on worker safety |  |  | 5450400000 | [6 empty] | 5450400000 | [20 empty] | 5450400000 | 0
Op. 10-CNC machine (2 single-spindle) | Fri 11/03/22 | Fri 29/04/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [10 empty] | 611316864 | 914795136 | [15 empty] | 1526112000 | 0
Op. 20-Drilling machine | Thu 09/12/21 | Thu 27/01/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [7 empty] | 698523264 | 827588736 | [18 empty] | 1526112000 | 0
Op. 30-CNC machine (2 double-spindle) | Wed 30/03/22 | Wed 18/05/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [10 empty] | 44475264 | 915667200 | 565969536 | [14 empty] | 1526112000 | 0
Op. 40-CNC machine (2 double-spindle) | Wed 09/02/22 | Wed 30/03/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [9 empty] | 567713664 | 958398336 | [16 empty] | 1526112000 | 0
Op. 50-CNC machine (1 single-spindle and 2 double-spindle) | Fri 29/04/22 | Fri 17/06/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [11 empty] | 872064 | 959270400 | 565969536 | [13 empty] | 1526112000 | 0
Op. 60-Washing station | Wed 15/12/21 | Fri 14/01/22 | Team of Italian workers (4 workers each) | 176 hrs | 22 days | 959270400 | [7 empty] | 524110464 | 435159936 | [18 empty] | 959270400 | 0
Op. 70-Assembly station | Wed 26/01/22 | Fri 11/03/22 | Team of Italian workers (4 workers each) | 256 hrs | 32 days | 1395302400 | [8 empty] | 131681664 | 872064000 | 391556736 | [16 empty] | 1395302400 | 0
Op. 80-CNC machine (2 double-spindle) | Fri 11/03/22 | Fri 29/04/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [10 empty] | 611316864 | 914795136 | [15 empty] | 1526112000 | 0
Op. 90-CNC machine (3 double-spindle) | Fri 29/04/22 | Fri 17/06/22 | Team of Italian workers (4 workers each) | 280 hrs | 35 days | 1526112000 | [11 empty] | 872064 | 959270400 | 565969536 | [13 empty] | 1526112000 | 0
Op. 100-Washing station | Wed 15/12/21 | Fri 14/01/22 | Team of Italian workers (4 workers each) | 176 hrs | 22 days | 959270400 | [7 empty] | 524110464 | 435159936 | [18 empty] | 959270400 | 0
Op. 110-Assembly station | Wed 26/01/22 | Fri 11/03/22 | Team of Italian workers (4 workers each) | 256 hrs | 32 days | 1395302400 | [8 empty] | 131681664 | 872064000 | 391556736 | [16 empty] | 1395302400 | 0
Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Wed 18/05/22 | Wed 22/06/22 | Team of Italian workers (4 workers each) | 200 hrs | 25 days | 1090080000 | [12 empty] | 393300864 | 696779136 | [13 empty] | 1090080000 | 0
Line manufacturing ICT system installation | Wed 22/06/22 | Wed 13/07/22 | Software developer[200%] | 240 hrs | 15 days | 457833600 | [13 empty] | 183743885 | 274089715 | [12 empty] | 457833600 | 0
Preliminary line testing | Wed 13/07/22 | Mon 25/07/22 | Software developer[200%];Team of Italian workers (4 workers each)[200%] | 192 hrs | 8 days | 819740160 | [14 empty] | 819740160 | [12 empty] | 819740160 | 0
Line disassembling (for all equipment) | Mon 25/07/22 | Thu 18/08/22 | Team of Italian workers (4 workers each)[300%] | 432 hrs | 18 days | 2354572800 | [14 empty] | 525854592 | 1828718208 | [11 empty] | 2354572800 | 0
WORK IN VIETNAM | Fri 29/10/21 | Wed 21/12/22 | Interpreter (risk mitigation) | 6.285,04 hrs | 297,62 days? | 267069600 | [6 empty] | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | 19076400 | [7 empty] | 267069600 | 0
CIVIL WORKS ERECTION PHASE | Fri 29/10/21 | Mon 19/09/22 | Insurance on typhoons | 3.843,76 hrs | 231,3 days | 272520000 |  |  |  |  | 272520000 | [22 empty] | 272520000 | 0
|  |  | Wall and drainage system (risk mitigation) |  |  | 3891585600 | [5 empty] | 3891585600 | [21 empty] | 3891585600 | 0
|  |  | Control meeting (risk mitigation) |  |  | 27252000 | [5 empty] | 13626000 |  |  |  |  | 13626000 | [16 empty] | 27252000 | 0
|  |  | Formation course (risk mitigation) | 3.888 hrs | 180 days | 13626000 | [5 empty] | 13626000 | [21 empty] | 13626000 | 0
|  |  | Option B (Addendum 3) |  |  | 35427000000 | [5 empty] | 35427000000 | [21 empty] | 35427000000 | 0
Site installation (working days) | Fri 29/10/21 | Fri 19/11/21 | Sub-contractor (Site installation) | 120 hrs | 15 days | 18347040000 | [5 empty] | 611568000 | 17735472000 | [20 empty] | 18347040000 | 0
Excavations & Foundations | Fri 19/11/21 | Wed 26/01/22 | Sub-contractor (Excavations & Foundations) | 384 hrs | 48 days | 39751920000 | [6 empty] | 6211237500 | 19047795000 | 14492887500 | [18 empty] | 39751920000 | 0
Structures | Tue 07/12/21 | Tue 01/03/22 | Sub-contractor (Structures) | 480 hrs | 60 days | 122313600000 | [7 empty] | 37713360000 | 42809760000 | 40771200000 | 1019280000 | [16 empty] | 122313600000 | 0
Roofing | Tue 28/12/21 | Tue 22/03/22 | Sub-contractor (Roofing) | 480 hrs | 60 days | 61156800000 | [7 empty] | 3567480000 | 21404880000 | 20385600000 | 15798840000 | [16 empty] | 61156800000 | 0
Enclosures | Tue 18/01/22 | Mon 31/01/22 | Sub-contractor (Enclosures) | 75,76 hrs | 9,47 days | 1266455400 | [8 empty] | 1266455400 | [18 empty] | 1266455400 | 0
Industrial flooring | Thu 20/01/22 | Tue 29/03/22 | Sub-contractor (Industrial flooring) | 384 hrs | 48 days | 48925440000 | [8 empty] | 7338816000 | 20385600000 | 21201024000 | [16 empty] | 48925440000 | 0
Building services | Mon 07/02/22 | Mon 19/09/22 | Sub-contractor (Building services) | 1.280 hrs | 160 days | 103966560000 | [9 empty] | 9876823200 | 14945193000 | 13645611000 | 14295402000 | 14295402000 | 13645611000 | 14945193000 | 8317324800 | [10 empty] | 103966560000 | 0
Finishes | Mon 30/05/2022 | Mon 19/09/2022 | Sub-contractor (Finishes) | 640 hrs | 80 days | 33636240000 | [12 empty] | 504543600 | 9249966000 | 8829513000 | 9670419000 | 5381798400 | [10 empty] | 33636240000 | 0
TRANSPORTATION PHASE | Mon 15/08/22 | Mon 24/10/22 |  | 600 hrs | 50,93 days | [28 empty] | 0 | 0
Ship trasportation | Mon 15/08/22 | Fri 16/09/22 | Ship;Double-spindle CNC machine trasportation[6];Final washing station trasportation[1];Gantry loader (including robots) trasportation[1];Metal footbridge trasportation[1];Single-spindle CNC machine trasportation[3];Protection grids including doors tras... | 200 hrs | 25 days | 835273800 | [15 empty] | 0 | 835273800 | [10 empty] | 835273800 | 0
Ship trasportation | Mon 05/09/22 | Fri 07/10/22 | Ship;Assembly station trasportation[1];Double-spindle CNC machine trasportation[5];Intermediate washing station trasportation[1] | 200 hrs | 25 days | 535501800 | [16 empty] | 0 | 535501800 | [9 empty] | 535501800 | 0
Ship trasportation | Mon 19/09/22 | Mon 24/10/22 | Ship;Assembly station trasportation[1];Drilling machine trasportation[1];Lift/lower component trasportation[1];Manipulator trasportation[2];Overhead conveyor trasportation[1];Powered conveyor trasportation[1];Rotating table trasportation[7] | 200 hrs | 25 days | 602269200 | [16 empty] | 0 | 602269200 | [9 empty] | 602269200 | 0
ON SITE ERECTION | Mon 19/09/22 | Wed 21/12/22 | Formation course (risk mitigation) | 3.888 hrs | 180 days | 13626000 | [6 empty] | 13626000 | [20 empty] | 13626000 | 0
|  |  | Control meeting (risk mitigation) |  |  | 27252000 | [16 empty] | 13626000 |  | 13626000 | [8 empty] | 27252000 | 0
Op. 10-CNC machine (2 single-spindle) | Mon 19/09/22 | Mon 10/10/22 | Team of Vietnamese workers (4 workers each) | 121,2 hrs | 15,15 days | 156481320 | [16 empty] | 95024960 | 61456360 | [9 empty] | 156481320 | 0
Op. 20-Drilling machine | Thu 27/10/22 | Mon 21/11/22 | Team of Vietnamese workers (4 workers each) | 129,52 hrs | 16,19 days | 167223272 | [17 empty] | 21380616 | 145842656 | [8 empty] | 167223272 | 0
Op. 30-CNC machine (2 double-spindle) | Mon 19/09/22 | Mon 10/10/22 | Team of Vietnamese workers (4 workers each) | 121,2 hrs | 15,15 days | 156481320 | [16 empty] | 95024960 | 61456360 | [9 empty] | 156481320 | 0
Op. 40-CNC machine (2 double-spindle) | Mon 10/10/22 | Thu 27/10/22 | Team of Vietnamese workers (4 workers each) | 103,84 hrs | 12,98 days | 134067824 | [17 empty] | 134067824 | [9 empty] | 134067824 | 0
Op. 50-CNC machine (1 single-spindle and 2 double-spindle) | Mon 19/09/22 | Mon 10/10/22 | Team of Vietnamese workers (4 workers each) | 121,2 hrs | 15,15 days | 156481320 | [16 empty] | 95024960 | 61456360 | [9 empty] | 156481320 | 0
Op. 60-Washing station | Mon 10/10/22 | Thu 27/10/22 | Team of Vietnamese workers (4 workers each) | 103,84 hrs | 12,98 days | 134067824 | [17 empty] | 134067824 | [9 empty] | 134067824 | 0
Op. 70-Assembly station | Mon 10/10/22 | Fri 04/11/22 | Team of Vietnamese workers (4 workers each) | 145,44 hrs | 18,18 days | 187777584 | [17 empty] | 155448440 | 32329144 | [8 empty] | 187777584 | 0
Op. 80-CNC machine (2 double-spindle) | Mon 19/09/22 | Mon 10/10/22 | Team of Vietnamese workers (4 workers each) | 121,2 hrs | 15,15 days | 156481320 | [16 empty] | 95024960 | 61456360 | [9 empty] | 156481320 | 0
Op. 90-CNC machine (3 double-spindle) | Mon 10/10/22 | Thu 27/10/22 | Team of Vietnamese workers (4 workers each) | 103,84 hrs | 12,98 days | 134067824 | [17 empty] | 134067824 | [9 empty] | 134067824 | 0
Op. 100-Washing station | Mon 19/09/22 | Mon 10/10/22 | Team of Vietnamese workers (4 workers each) | 121,2 hrs | 15,15 days | 156481320 | [16 empty] | 95024960 | 61456360 | [9 empty] | 156481320 | 0
Op. 110-Assembly station | Thu 27/10/22 | Thu 17/11/22 | Team of Vietnamese workers (4 workers each) | 119,28 hrs | 14,91 days | 154002408 | [17 empty] | 21380616 | 132621792 | [8 empty] | 154002408 | 0
Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Thu 27/10/22 | Mon 21/11/22 | Team of Vietnamese workers (4 workers each) | 129,52 hrs | 16,19 days | 167223272 | [17 empty] | 21380616 | 145842656 | [8 empty] | 167223272 | 0
Line manufacturing ICT system installation | Mon 21/11/22 | Mon 12/12/22 | Software developer[200%];Software developer travel cost[30] | 240 hrs | 15 days | 572292000 | [18 empty] | 300644064 | 271647936 | [7 empty] | 572292000 | 0
Test on Completion | Mon 12/12/22 | Wed 21/12/22 | Software developer[200%];Software developer travel cost[6] |  |  | 114458400 | [19 empty] | 114458400 | [7 empty] | 114458400
|  |  | Team of Vietnamese workers (4 workers each)[200%] | 160 hrs | 7 days? | 144603200 | [19 empty] | 144603200 | [7 empty] | 144603200 | 0
ACCEPTANCE OF THE WORK | Wed 21/12/22 | Wed 18/01/23 |  | 640 hrs | 20 days? | [28 empty] | 0 | 0
TEST AFTER COMPLETION | Wed 21/12/22 | Mon 02/01/23 | Installation supervisor;Project engineer[200%];Software developer[200%];Team of Vietnamese workers (4 workers each)[200%];Installation supervisor travel cost[8];Project engineer travel cost[16];Software developer travel cost[16] | 448 hrs | 8 days | 998081920 | [19 empty] | 983110691 | 14971229 | [6 empty] | 998081920 | 0
OWNER'S TAKING OVER | Mon 02/01/23 | Wed 18/01/23 |  | 192 hrs | 12 days? | [28 empty] | 0 | 0
SUBMISSION OF TECHNICAL DOCUMENTATION | Mon 02/01/23 | Fri 13/01/23 | Project engineer[200%];Project engineer travel cost[18] | 144 hrs | 9 days? | 441482400 | [20 empty] | 441482400 | [6 empty] | 441482400 | 0
Line Delivery | Fri 13/01/23 | Wed 18/01/23 | Project engineer;Software developer;Project engineer travel cost[3];Software developer travel cost[3] | 48 hrs | 3 days | 130809600 | [20 empty] | 130809600 | [6 empty] | 130809600 | 0
MANAGEMENT | Wed 09/06/21 | Wed 21/12/22 |  | 5.351,28 hrs | 400,11 days? | [28 empty] | 0 | 0
Project management | Wed 09/06/21 | Tue 30/11/21 | Project manager | 1.000 hrs | 125 days? | 3661033680 |  | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 177138000 | 184223520 | 192944160 | 192944160 | 192944160 | 192944160 | 225101520 | [6 empty] | 3661033680 | 0
Site Management | Fri 29/10/21 | Wed 21/12/22 | Site manager;Site manager travel cost[298] | 2.380,88 hrs | 297,61 days | 4372688404 | [5 empty] | 7346340 | 323238953 | 337931633 | 308546274 | 293853594 | 337931633 | 308546274 | 323238953 | 323238953 | 308546274 | 337931633 | 323238953 | 308546274 | 323238953 | 207313711 | [7 empty] | 4372688405 | 0
Supervision to pre-erection | Thu 09/12/21 | Thu 18/08/22 | Installation supervisor | 1.439,92 hrs | 179,99 days | 2354441990 | [7 empty] | 209556979 | 274700160 | 261619200 | 300862080 | 274700160 | 287781120 | 287781120 | 274700160 | 182741011 | [11 empty] | 2354441990 | 0
Supervision to on site erection | Mon 19/09/22 | Wed 21/12/22 | Installation supervisor;Installation supervisor travel cost[67] | 530,48 hrs | 66,31 days | 1123022218 | [16 empty] | 155810653 | 355654752 | 372590692 | 238966121 | [7 empty] | 1123022218 | 0
End | Wed 18/01/23 | Wed 18/01/23 |  | 0 hrs | 0 days | [28 empty] | 0 | 0
|  |  | HR TOT |  |  | 40088564732 | 28342080 | 1589881680 | 1818798480 | 2312877240 | 802298880 | 211736340 | 546705353 | 2490447204 | 2740732770 | 3063528858 | 3857254913 | 3526462434 | 3685045673 | 2819696566 | 2399145301 | 2552690772 | 704696166 | 876221586 | 1222120269 | 2027517419 | 812364749 | 0 | 0 | 0 | 0 | 0 | 0 | 40088564733 | 0
|  |  | MATERIALS TOT |  |  | 315396661680 | 0 | 0 | 0 | 2823390412 | 1427921588 | 0 | 8819837280 | 48236040000 | 62570592000 | 27252000000 | 86871200400 | 77395680000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 315396661680 | 0
|  |  | SUBCONTRACTORS TOT |  |  | 472661125608 | 0 | 0 | 0 | 0 | 0 | 39930153600 | 23946709500 | 60328635000 | 87312798900 | 91419223200 | 52964337000 | 13645611000 | 14799945600 | 23545368000 | 22475124000 | 24615612000 | 15009521800 | 2066846560 | 456636248 | 144603200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 472661125608 | 0
|  |  | OVERHEAD TOT |  |  | 93310848000 | 218016000 | 4796352000 | 4796352000 | 4796352000 | 4796352000 | 4578336000 | 4796352000 | 5014368000 | 4578336000 | 4360320000 | 5014368000 | 4578336000 | 4796352000 | 4796352000 | 4578336000 | 5014368000 | 4796352000 | 4578336000 | 4796352000 | 4796352000 | 2834208000 | 0 | 0 | 0 | 0 | 0 | 0 | 93310848000 | 0
|  |  | INSURANCE |  |  | 5722920000 | 0 | 0 | 0 | 0 | 272520000 | 0 | 5450400000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5722920000 | 0
|  |  | TOTAL |  |  | 927180120020 | 246358080 | 6386233680 | 6615150480 | 9932619652 | 7299092468 | 44720225940 | 43560004133 | 116069490204 | 157202459670 | 126095072058 | 148707160313 | 99146089434 | 23281343273 | 31161416566 | 29452605301 | 32182670772 | 20510569966 | 7521404146 | 6475108517 | 6968472619 | 3646572749 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | CHECK TOTAL |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | COST MACHINE INSTALLED IN THIS MONTH | [19 empty] | 147423509280 | 163721840400
TOTAL CONSTRUCTION COST | 782520180888 |  | CONSTRUCTION COSTS |  |  |  | 0 | 0 | 0 | 0 | 0 | 39930153600 | 23946709500 | 60328635000 | 87312798900 | 91419223200 | 52964337000 | 13645611000 | 14799945600 | 23545368000 | 22475124000 | 24615612000 | 161597757280 | 164650915960 | 757280312 | 530709536 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | COMPLETING PERCENTAGE OF CONSTRUCTION WORKS |  |  |  | 0% | 0% | 0% | 0% | 0% | 5.103% | 8.163% | 15.87% | 27.03% | 38.71% | 45.48% | 47.23% | 49.12% | 52.13% | 55% | 58.14% | 78.79% | 99.84% | 99.93% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
|  |  | DELTA PERCENTAGE |  |  |  | 0% | 0% | 0% | 0% | 0% | 5.103% | 3.06% | 7.71% | 11.16% | 11.68% | 6.768% | 1.744% | 1.891% | 3.009% | 2.872% | 3.146% | 20.65% | 21.04% | 0.09677% | 0.06782% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Price calculation
Direct Costs | 833869272021 | 30598461.4715
Human Resources | 40088564733 | 1471032.0245
Cost of material | 315396661680 | 11573340
Subcontractors | 472661125608 | 17344089.4469
Insurances | 5722920000 | 210000
Overhead | 93310848000 | 3424000
Contingency Budget | 45541475499.312 | 1671124.156
Interest | 7431265073.3846 | 272686.9614
Total Costs | 980152860593.6967 | 35966272.5889
Profit Margin | 117618343271.2436 | 4315952.7107
Price | 1.0978e+12 | 40282225.2996