## Sheet1
|  | Normal situation (without considering the risks) | [5 empty] | Risk analysis
SCENARIO | TOTAL DURATION | TOTAL NORMAL COST | NORMAL DIRECT COST | NORMAL OVERHEAD COST | NORMAL DURATION | NORMAL COST VARIATION | NORMAL DURATION VARIATION | RBM (RISK COST + OVERHEAD COST + MITIGATION) | RISK COST | RBM OVERHEAD COST | RBM TOTAL DURATION | RISK MITIGATION COST
BASIC SCENARIO (AFTER FAQ) | 601.97 | 921929845860 | 790690754340 | 131239091520 | 601.97 | 0 | 0
BASIC SCENARIO + OPTION A | 484.5 | 921843129996 | 816214377996 | 105628752000 | 484.5 | -86715864 | -117.47
BASIC SCENARIO + OPTION B | 432.8 | 917986208940 | 823628884140 | 94357324800 | 432.8 | -3943636920 | -169.17
BEST SCENARIO (option B + crash on Vietnamese teams) | 427.12 | 917011295892 | 823892301972 | 93118993920 | 427.12 | -4918549968 | -174.85
BEST SCENARIO WITH RISKS, BEFORE MITIGATION | 494.2329 | 917011295892 | 823892301972 | 93118993920 | 427.12 |  |  | 76433285505.07 | 61801599498.67 | 14631686006.4 | 67.1129 | 0
BEST SCENARIO WITH RISK COST AND RISK MITIGATION | 478.9684 | 917011295892 | 823892301972 | 93118993920 | 427.12 |  |  | 50022664036.85 | 28741926062.45 | 11303780774.4 | 51.8484 | 9976957200
Comment on the table of changes in costs and durations based on the scenarios
From the basic scenario we tried to test option A and option B
Maritime transport is not on the critical path so it is not necessary to use air transport as it will only increase the costs
We saw that option B is convenient and therefore crashed on Vietnamese teams
We continued our analysis adding the cost of risks and the duration due to the realization of the risks
We have mitigated risks, thereby reducing the cost and duration of the risks
Through the choice of Option B and the crashing we were able to reduce the total duration of the project so that the increase of direct costs remains lower than the decrease in indirect costs | [5 empty] | Through risk mitigation, we were able to reduce the probability and impact of each risk, thus reducing the maximum delay and the economic impact of the risks