## Tasks
EXHIBIT 3
TASKS AND RESOURCES
No | TASK NAME | RESOURCE NAME | WORK | DURATION | UNITS | PARAMETER COST
|  |  | hour | working day | # | VND/m2
0 | START-UP
| Contract finalization and signature | Project Manager | 16 |  | 1
| Detailed Planning | Project Manager |  | 5 | 1
1 | ENGINEERING PHASE
| Detailed Engineering - Process | Project Engineer | 210 |  | 2
|  | Specialized Engineer | 140 |  | 1-2
| Detailed Engineering - Layout | Project Engineer | 150 |  | 2
|  | Specialized Engineer | 110 |  | 1-2
| Detailed Engineering - Utilities | Project Engineer | 120 |  | 2
|  | Specialized Engineer | 90 |  | 2
| Industrial Building Design | Project Engineer | 300 |  | 2
|  | Specialized Engineer | 210 |  | 1-2
| Line manufacturing ICT system specification & development | Software Engineer | 210 |  | 3
|  | Software Developer | 400 |  | 2
| Approval of engineering by the client | Owner |  | 20 | -
| Permits and authorizations from local authorities | Project engineer | 160 | 90 | 2
|  | Specialized engineer | 120 |  | 2
2 | PURCHASE PHASE (values for each lot of equipment)
| Request for proposals | Purchasing Agent | 40 |  | 2
| Collection of proposals |  |  | 20 | -
| Competitive proposal analysis | Purchasing Agent | 32 |  | 1-2
|  | Project Engineer | 32 |  | 2
| Orders | Purchasing Agent | 16 |  | 1-2
3 | EQUIPMENT MANUFACTURING PHASE (values for each unit of equipment including transportation)
| CNC machine (single-spindle and double-spindle) | Supplier |  | 110 | -
| Washing station | Supplier |  | 70 | -
| Drilling machine | Supplier |  | 66 | -
| Assembly station | Supplier |  | 100 | -
| Gantry loaders and robotized arms (total values) | Supplier |  | 95 | -
| Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Supplier |  | 130 | -
| Metal foodbridges and protection grids (total values) | Supplier |  | 40 | -
4 | PRE- ERECTION PHASE (values for each operation)
| Op. 10-30-40-50-80-90, including all CNC machine (single-spindle and double-spindle) and the associated gantry loaders, metal foodbridges, and protection grids | Team of Italian workers |  | 35 | 1
| Op. 60-100, Washing station | Team of Italian workers |  | 22 | 1
| Op. 20, Drilling machine | Team of Italian workers |  | 35 | 1
| Op. 70-110, Assembly station | Team of Italian workers |  | 32 | 1
| Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Team of Italian workers |  | 25 | 1
| Line manufacturing ICT system installation | Software Developer |  | 15 | 2
| Preliminary line testing | Team of Italian workers |  | 8 | 2
|  | Software Developer |  | 4 | 2
| Line disassembling (for all equipment) | Team of Italian workers |  | 18 | 3
5 | TRANSPORTATION PHASE (from the contractor to the owner's construction site)
| See Request for Proposal | Logistics Service Provider
6 | CIVIL WORKS ERECTION PHASE
| Site installation (working days) | Sub-contractor |  | 15 |  | 764460
| Excavations & Foundations | Sub-contractor |  | 1/500m2 |  | 1656330
| Structures | Sub-contractor |  | 1/400m2 |  | 5096400
| Roofing | Sub-contractor |  | 1/400m2 |  | 2548200
| Enclosures | Sub-contractor |  | 1/75 lm |  | 1783740
| Industrial flooring | Sub-contractor |  | 1/500m2 |  | 2038560
| Building services | Sub-contractor |  | 1/150m2 |  | 4331940
| Finishes | Sub-contractor |  | 1/300m2 |  | 1401510
7 | ON SITE ERECTION PHASE (values for each operation)
| Op. 10-30-40-50-80-90, including all CNC machine (single-spindle and double-spindle) and the associated gantry loaders, metal foodbridges, and protection grids | Team of Vietnamese workers |  | 10 | 1
| Op. 60-100, Washing station | Team of Vietnamese workers |  | 10 | 1
| Op. 20-Drilling machine | Team of Vietnamese workers |  | 15 | 1
| Op. 70-110, Assembly station | Team of Vietnamese workers |  | 14 | 1
| Material handling equipment (powered conveyors, overhead conveyors, lift/lower components, manipulators, rotating tables). Total values | Team of Vietnamese workers |  | 15 | 1
| Line manufacturing ICT system installation | Software Developer |  | 15 | 2
| Test on Completion | Team of Vietnamese workers |  | 7 | 2
|  | Software Developer |  | 3 | 2
9 | TEST AFTER COMPLETION
|  | Project Engineer |  | 8 | 2
|  | Software Developer |  | 8 | 2
|  | Team of Vietnamese workers |  | 8 | 2
|  | Installation Supervisor |  | 8 | 1
10 | OWNER'S TAKING OVER
| SUBMISSION OF TECHNICAL DOCUMENTATION | Project Engineer | 144 |  | 2
| Line Delivery | Project Engineer |  | 3 | 1
|  | Software Developer |  | 3 | 1
11 | MANAGEMENT
| Project Management | Project Manager | 1000 | As long as the project duration | 1
| Site Management | Site Manager |  | As long as the total duration of the on-site activities | 1
| Supervision to pre-erection | Installation Supervisor |  | As long as the total duration of the pre-erection phase | 1
| Supervision to on site erection | Installation Supervisor |  | As long as the total duration of the on site erection phase | 1
NOTE. The machine manufacturing and erection durations do include the manufacturing and erection durations of the associated utility systems
Note on B26: Giovanni Zenezini: ne facciamo soltanto una? oppure una per lavori civili e una per impianti/attrezzature

## Resources
Resource name | Unit cost/hour | Currency | max available units
Project manager | 130 | € | 1
Site manager | 1359050 | VND (Vietnamese Dong) | 1
Installation supervisor | 60 | € | 1
Team of Vietnamese workers (4 workers each) | 1291100 | VND (Vietnamese Dong) | 3 normal case 6 crashed case
Team of Italian workers (4 workers each) | 200 | € | 3
Project engineer | 95 | € | 2
Specialized engineer | 80 | € | 4
Purchasing agent | 70 | € | 4
Software engineer | 85 | € | 6
Software developer | 70 | € | 2

## Equipment
EQUIPMENT IN THE SCOPE OF THE SUPPLY | UNIT COST (*) | TRANSPORTATION COST-SHIP (**)
| [€/unit] | [€/unit]
Single-spindle CNC machine | 340000 | 1780
Double-spindle CNC machine | 500000 | 2860
Intermediate washing station | 530000 | 2000
Final washing station | 970000 | 3150
Drilling machine | 270000 | 1800
Assembly station | 1100000 | 3350
Manipulator | 11000 | 1000
Gantry loader (including robots) | 96000 | 750
Powered conveyor | 282000 | 3600
Rotating table | 16000 | 1200
Overhead conveyor | 75500 | 1550
Lift/lower component | 16200 | 1400
Metal footbridge | 2200 | 500
Protection grids including doors | 321440 | 3750
Utilities systems | Included in the machine cost
Line manufacturing ICT system | 156000 | -
(*) All the unit costs, except for the line manufacturing ICT system, do include the transportation cost from the supplier to the Contractor.
(**) Transportation costs from the Contractor's site to the Owner's site.